HHS Summer Numeracy School.

Communications with schools, pupils and parents.

| # Things to do | ## Who? | Date(s) |  |
| --- | --- | --- | --- |
| Send letter to Feeder Schools. Details of summer school. Criteria for pupils. Request 3 pupils + 1/2 reserves. | GFe | WB 15th May |  |
| Phone Feeder Schools. Answer any questions. | GFe | WB 22nd May |  |
| Visit Feeder Schools. Talk with Head Teachers. Promote the Numeracy school. Collect pupil names. Leave pupil information forms to collect later. | See list of schools | WB 5th June |  |
| Visit pupils at Feeder School. Talk to pupils to explain. Get pupils excited about the Numeracy school. Hand out provisional timetable. | See list of schools | WB 19th June WB 26th June |  |
| Write to parents. Details of the Numeracy school. Examples of activities. Emergency contact. Invite child to attend. Reply slips. | LDt | WB 26th June |  |
| Collect reply slips from schools. Collect reply slips. Collect pupil information forms. | See list of schools | WB 3rd July |  |
| Write to parents. Confirm place on Numeracy school. | GFe | WB 10th July |  |
| Phone parents. Check everything is OK. Confirm time/place for pick-up. Invitation to visit Numeracy school. | GFe LDt | Thursday 27th – Saturday 29th July |  |
| NUMERACY SCHOOL BEGINS. | All Staff. | Monday 31st July |  |

HHS Summer Numeracy School.

Feeder School Visits:

| # School | Staff |
| --- | --- |
| # Bell Lane, Ackworth. |  |
| Mill Dam, Ackworth. |  |
| West End, Hemsworth. |  |
| St. Helen’s, Hemsworth. |  |
| Grove Lea, Hemsworth. |  |
| South Heindley. |  |
| Havercroft. |  |
| Ryhill. |  |
| Kinsley. |  |
| Fitzwilliam. |  |